## July 2017 draft
NUMBER OF CONSUMERS TRANSITIONING INTO THE COMMUNITY FROM DEVELOPMENTAL CENTERS SUBJECT TO CLOSURE PROJECTED AND ACTUAL TRANSITIONS
July 2017 projected and actual; August 2017 projected
Transitions are projected for individual consumers based on scheduled or projected transition review meetings.
TABLE 2A: ALL DEVELOPMENTAL CENTERS
Developmental Center | Fiscal Year 2017-18 |  |  | July 2017 |  | August 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions 1 Through July 2017 | Remaining Transitions 1 | Projected | Actual | Projected
FDC - Fairview | 95 | 3 | 93 | 3 | 3 | 3
PDC - Porterville | 32 | 3 | 29 | 3 | 3 | 1
SDC - Sonoma | 184 | 1 | 183 | 3 | 1 | 6
TOTAL 1 | 311 | 7 | 305 | 9 | 7 | 10
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers and the secure treatment program.
1 Includes a consumer placed from FDLRC who later returned to FDC and needs new community placement.
TABLE 2B: FAIRVIEW DEVELOPMENTAL CENTER
In Fiscal Year 2017-18 through July 2017, 3 consumers have transitioned from Fairview Developmental Center (FDC) to the community.
In July 2017, 3 consumers from FDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 3 consumers from FDC would transition to the community in July 2017.
Regional Center | Fiscal Year 2017-18 |  |  | July 2017 |  | August 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions 1 Through July 2017 | Remaining Transitions 1 | Projected | Actual | Projected
ACRC - Alta California | 1 | 0 | 1 | 0 | 0 | 0
ELARC - Eastern Los Angeles | 5 | 0 | 5 | 0 | 0 | 0
FDLRC - Frank D. Lanterman | 2 | 0 | 3 | 0 | 0 | 0
HRC - Harbor | 3 | 0 | 3 | 0 | 0 | 1
IRC - Inland | 4 | 0 | 4 | 0 | 0 | 1
NLACRC - North Los Angeles County | 6 | 0 | 6 | 0 | 0 | 0
RCOC - Orange County | 35 | 0 | 35 | 0 | 0 | 0
SARC - San Andreas | 1 | 0 | 1 | 0 | 0 | 0
SCLARC - South Central Los Angeles | 7 | 1 | 6 | 1 | 1 | 1
SDRC - San Diego | 15 | 1 | 14 | 1 | 1 | 0
SGPRC - San Gabriel/Pomona | 5 | 0 | 5 | 0 | 0 | 0
TCRC - Tri-Counties | 5 | 0 | 5 | 0 | 0 | 0
WRC - Westside | 6 | 1 | 5 | 1 | 1 | 0
TOTAL 1 | 95 | 3 | 93 | 3 | 3 | 3
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in the acute crisis center.
1 Includes a consumer placed from FDLRC who later returned to FDC and needs a new community placement.
TABLE 2C: PORTERVILLE DEVELOPMENTAL CENTER
In Fiscal Year 2017-18 through July 2017, 3 consumers have transitioned from Porterville Developmental Center (PDC) to the community.
In July 2017, 3 consumers from PDC's General Treatment Area transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 3 consumers from FDC would transition to the community in July 2017.
Regional Center | Fiscal Year 2017-18 |  |  | July 2017 |  | August 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through July 2017 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 1 | 1 | 0 | 1 | 1 | 0
CVRC - Central Valley | 10 | 1 | 9 | 1 | 1 | 1
FNRC - Far Northern | 1 | 0 | 1 | 0 | 0 | 0
IRC - Inland | 1 | 0 | 1 | 0 | 0 | 0
KRC - Kern | 7 | 1 | 6 | 1 | 1 | 0
NLACRC - North Los Angeles County | 1 | 0 | 1 | 0 | 0 | 0
RCRC - Redwood Coast | 1 | 0 | 1 | 0 | 0 | 0
SARC - San Andreas | 2 | 0 | 2 | 0 | 0 | 0
SCLARC - South Central Los Angeles | 3 | 0 | 3 | 0 | 0 | 0
TCRC - Tri-Counties | 1 | 0 | 1 | 0 | 0 | 0
VMRC - Valley Mountain | 3 | 0 | 3 | 0 | 0 | 0
WRC - Westside | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 32 | 3 | 29 | 3 | 3 | 1
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Notes: Excludes consumers in the secure treatment program.
TABLE 2D: SONOMA DEVELOPMENTAL CENTER
In Fiscal Year 2017-18 through July 2017, 1 consumer have transitioned from Sonoma Developmental Center (SDC) to the community.
In July 2017, 1 consumer from SDC transitioned to the community. In the previous month, Regional Centers had projected that 3 consumers from SDC would transition to the community in July 2017. One consumer’s transition was delayed until August while licensing was completed, and one will move in September when the home and staff are ready.
Regional Center | Fiscal Year 2017-18 |  |  | July 2017 |  | August 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through July 2017 | Remaining Transitions | Projected | Actual A | Projected
ACRC - Alta California | 27 | 1 | 26 | 1 | 1 | 1
CVRC - Central Valley | 2 | 0 | 2 | 0 | 0 | 0
FNRC - Far Northern | 4 | 0 | 4 | 0 | 0 | 0
GGRC - Golden Gate | 30 | 0 | 30 | 1 | 0 | 3
NBRC - North Bay | 57 | 0 | 57 | 1 | 0 | 0
RCEB - East Bay | 58 | 0 | 58 | 0 | 0 | 1
RCRC - Redwood Coast | 2 | 0 | 2 | 0 | 0 | 0
SARC - San Andreas | 3 | 0 | 3 | 0 | 0 | 1
VMRC - Valley Mountain | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 184 | 1 | 183 | 3 | 1 | 6
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in the acute crisis center.