## Transitions
NUMBER OF CONSUMERS TRANSITIONING INTO THE COMMUNITY FROM DEVELOPMENTAL CENTERS SUBJECT TO CLOSURE PROJECTED AND ACTUAL TRANSITIONS
March 2017 projected and actual; April 2017 projected
Transitions are projected for individual consumers based on scheduled or projected transition review meetings.
TABLE 2A: ALL DEVELOPMENTAL CENTERS
Developmental Center | Fiscal Year 2016-17 |  |  | March 2017 |  | April 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through March 2017 | Remaining Transitions | Projected | Actual | Projected
FDC - Fairview | 81 | 34 | 47 | 6 | 8 | 2
PDC - Porterville | 34 | 21 | 13 | 2 | 3 | 2
SDC - Sonoma | 84 | 52 | 32 | 6 | 11 | 9
TOTAL | 199 | 107 | 92 | 14 | 22 | 13
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers and the secure treatment program.
TABLE 2B: FAIRVIEW DEVELOPMENTAL CENTER
In FY 2016-17 through March 2017, 34 consumers have transitioned from Fairview Developmental Center (FDC) to the community.
In March 2017, 8 consumers from FDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 6 consumers from FDC would transition to the community in March 2017.
Regional Center | Fiscal Year 2016-17 |  |  | March 2017 |  | April 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through March 2017 | Remaining Transitions | Projected | Actual | Projected
ELARC - Eastern Los Angeles | 9 | 1 | 8 | 0 | 0 | 1
FDLRC - Frank D. Lanterman | 4 | 0 | 4 | 0 | 0 | 0
HRC - Harbor | 7 | 4 | 3 | 1 | 1 | 0
IRC - Inland | 2 | 1 | 1 | 0 | 0 | 1
KRC - Kern | 0 | 0 | 0 | 0 | 0 | 0
NLACRC - North Los Angeles County | 10 | 8 | 2 | 1 | 1 | 0
RCOC - Orange County | 13 | 8 | 5 | 1 | 1 | 0
SARC - San Andreas | 1 | 0 | 1 | 0 | 0 | 0
SCLARC - South Central Los Angeles | 3 | 5 | -2 | 3 | 3 | 0
SDRC - San Diego | 16 | 2 | 14 | 0 | 1 | 0
SGPRC - San Gabriel/Pomona | 7 | 4 | 3 | 0 | 0 | 0
TCRC - Tri-Counties | 4 | 1 | 3 | 0 | 1 | 0
VMRC - Valley Mountain | 5 | 0 | 5 | 0 | 0 | 0
TOTAL | 81 | 34 | 47 | 6 | 8 | 2
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in the acute crisis center. ( ) indicates that total transitions exceed the CPP projection.
TABLE 2C: PORTERVILLE DEVELOPMENTAL CENTER
In FY 2016-17 through March 2017, 21 consumers have transitioned from Porterville Developmental Center (PDC) to the community.
In March 2017, 3 consumer from PDC's General Treatment Area transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 2 consumers from FDC would transition to the community in March 2017.
Regional Center | Fiscal Year 2016-17 |  |  | March 2017 |  | April 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through March 2017 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 2 | 0 | 2 | 0 | 0 | 0
CVRC - Central Valley | 17 | 10 | 7 | 1 | 2 | 1
FDLRC - Frank D. Lanterman | 1 | 0 | 1 | 0 | 0 | 0
FNRC - Far Northern | 2 | 0 | 2 | 0 | 0 | 0
GGRC - Golden Gate | 1 | 1 | 0 | 0 | 1 | 0
IRC - Inland | 1 | 0 | 1 | 0 | 0 | 0
KRC - Kern | 7 | 9 | -2 | 1 | 0 | 0
NLACRC - North Los Angeles County | 0 | 1 | -1 | 0 | 0 | 0
TCRC - Tri-Counties | 0 | 0 | 0 | 0 | 0 | 1
VMRC - Valley Mountain | 3 | 0 | 3 | 0 | 0 | 0
TOTAL | 34 | 21 | 13 | 2 | 3 | 2
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Notes: Excludes consumers in the secure treatment program. ( ) indicates that total transitions exceed the CPP projection.
TABLE 2D: SONOMA DEVELOPMENTAL CENTER
In FY 2016-17 through March 2017, 52 consumers have transitioned from Sonoma Developmental Center (SDC) to the community.
In March 2017, 11 consumers from SDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 6 consumers from SDC would transition to the community in March 2017.
Regional Center | Fiscal Year 2016-17 |  |  | March 2017 |  | April 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through March 2017 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 17 | 7 | 10 | 1 | 2 | 3
FNRC - Far Northern | 2 | 3 | -1 | 0 | 1 | 0
GGRC - Golden Gate | 20 | 12 | 8 | 1 | 2 | 1
NBRC - North Bay | 22 | 14 | 8 | 2 | 3 | 3
RCEB - East Bay | 19 | 10 | 9 | 2 | 3 | 1
RCRC - Redwood Coast | 1 | 1 | 0 | 0 | 0 | 1
SARC - San Andreas | 0 | 1 | -1 | 0 | 0 | 0
SDRC - San Diego | 0 | 1 | -1 | 0 | 0 | 0
TCRC - Tri-Counties | 2 | 3 | -1 | 0 | 0 | 0
VMRC - Valley Mountain | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 84 | 52 | 32 | 6 | 11 | 9
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Notes: Excludes consumers in the acute crisis center. ( ) indicates that total transitions exceed the CPP projection.