## Transitions
NUMBER OF CONSUMERS TRANSITIONING INTO THE COMMUNITY FROM DEVELOPMENTAL CENTERS SUBJECT TO CLOSURE PROJECTED AND ACTUAL TRANSITIONS
Transitions are projected for individual consumers based on scheduled or projected transition review meetings.
TABLE 2A: ALL DEVELOPMENTAL CENTERS
Developmental Center | Fiscal Year 2016-17 |  |  | November 2016 |  | December 2016
| Approved Community Placement Plan Transitions | Total Transitions Through November 2016 1 | Remaining Transitions | Projected | Actual | Projected
FDC - Fairview | 81 | 20 | 62 | 0 | 8 | 6
PDC - Porterville | 34 | 12 | 22 | 0 | 4 | 2
SDC - Sonoma | 84 | 15 | 69 | 10 | 7 | 12
TOTAL | 199 | 47 | 153 | 10 | 19 | 20
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers and the secure treatment program.
1 Includes one FDC consumer from SDRC who transitioned into the community on November 29, 2016 and returned on December 1, 2016.
TABLE 2B: FAIRVIEW DEVELOPMENTAL CENTER
In FY 2016-17 through November 2016, 20 consumers have transitioned from Fairview Developmental Center (FDC) to the community.
In November 2016, 8 consumers from FDC transitioned to the community.
Beginning in December 2016, transition projections will be updated regularly for individual consumers.
Regional Center | Fiscal Year 2016-17 |  |  | November 2016 |  | December 2016
| Approved Community Placement Plan Transitions | Total Transitions Through November 2016 1 | Remaining Transitions | Projected | Actual | Projected
ELARC - Eastern Los Angeles | 9 | 0 | 9 | 0 | 0 | 2
FDLRC - Frank D. Lanterman | 4 | 0 | 4 | 0 | 0 | 0
HRC - Harbor | 7 | 3 | 4 | 0 | 1 | 0
IRC - Inland | 2 | 0 | 2 | 0 | 0 | 1
KRC - Kern | 0 | 0 | 0 | 0 | 0 | 1
NLACRC - North Los Angeles County | 10 | 4 | 6 | 0 | 1 | 2
RCOC - Orange County | 13 | 6 | 8 | 0 | 1 | 0
SARC - San Andreas | 1 | 0 | 1 | 0 | 0 | 0
SCLARC - South Central Los Angeles | 3 | 1 | 2 | 0 | 1 | 0
SDRC - San Diego | 16 | 3 | 13 | 0 | 3 | 0
SGPRC - San Gabriel/Pomona | 7 | 3 | 4 | 0 | 1 | 0
TCRC - Tri-Counties | 4 | 0 | 4 | 0 | 0 | 0
VMRC - Valley Mountain | 5 | 0 | 5 | 0 | 0 | 0
TOTAL | 81 | 20 | 62 | 0 | 8 | 6
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers.
1 Includes one FDC consumer from SDRC who transitioned into the community on November 29, 2016 and returned on December 1, 2016.
TABLE 2C: PORTERVILLE DEVELOPMENTAL CENTER
In FY 2016-17 through November 2016, 12 consumers have transitioned from Porterville Developmental Center (PDC) to the community.
In November 2016, 4 consumers from PDC transitioned to the community.
Beginning in December 2016, transition projections will be updated regularly for individual consumers.
Regional Center | Fiscal Year 2016-17 |  |  | November 2016 |  | December 2016
| Approved Community Placement Plan Transitions | Total Transitions Through November 2016 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 2 | 0 | 2 | 0 | 0 | 0
CVRC - Central Valley | 17 | 8 | 9 | 0 | 3 | 0
FDLRC - Frank D. Lanterman | 1 | 0 | 1 | 0 | 0 | 0
FNRC - Far Northern | 2 | 0 | 2 | 0 | 0 | 0
GGRC - Golden Gate | 1 | 0 | 1 | 0 | 0 | 0
IRC - Inland | 1 | 0 | 1 | 0 | 0 | 0
KRC - Kern | 7 | 4 | 3 | 0 | 1 | 2
VMRC - Valley Mountain | 3 | 0 | 3 | 0 | 0 | 0
TOTAL | 34 | 12 | 22 | 0 | 4 | 2
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in the secure treatment program.
TABLE 2D: SONOMA DEVELOPMENTAL CENTER
In FY 2016-17 through November 2016, 15 consumers have transitioned from Sonoma Developmental Center (SDC) to the community.
In November 2016, 7 consumers from SDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 10 consumers from SDC would transition to the community in November 2016. Three projected transitions were postponed for various reasons related to the scheduling of transition review meetings, including one at a family's request. One of the three transitions will occur in December 2016 and two in January 2017.
Regional Center | Fiscal Year 2016-17 |  |  | November 2016 |  | December 2016
| Approved Community Placement Plan Transitions | Total Transitions Through November 2016 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 17 | 1 | 16 | 0 | 0 | 3
FNRC - Far Northern | 2 | 0 | 2 | 0 | 0 | 1
GGRC - Golden Gate | 20 | 5 | 15 | 4 | 3 | 3
NBRC - North Bay | 22 | 2 | 20 | 3 | 2 | 3
RCEB - East Bay | 19 | 5 | 14 | 3 | 2 | 1
RCRC - Redwood Coast | 1 | 0 | 1 | 0 | 0 | 0
SARC - San Andreas | 0 | 0 | 0 | 0 | 0 | 0
TCRC - Tri-Counties | 2 | 2 | 0 | 0 | 0 | 1
VMRC - Valley Mountain | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 84 | 15 | 69 | 10 | 7 | 12
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers.