## Online Development Report v2
DEVELOPMENT OF RESIDENTIAL CAPACITY FOR CONSUMERS TRANSITIONING FROM
DEVELOPMENTAL CENTERS SUBJECT TO CLOSURE
2017-10-31
TABLE 1A: ALL DEVELOPMENTAL CENTERS
Developmental Center | Total Approved Start-Up Projects 1 |  | Number of Projects in Each Stage of Development
|  |  | Pre-Acquisition 2 | In Escrow 3 | Acquired and Under Renovation 4 |  | Pending Licensure 5 |  | Licensed, Vendored and Certified 6
| Projects | Capacity | Projects | Projects | Projects | Capacity | Projects | Capacity | Projects | Capacity
FDC - Fairview | 59 | 241 | 12 | 5 | 17 | 71 | 4 | 16 | 21 | 99
PDC - Porterville | 34 | 154 | 5 | 3 | 11 | 61 | 3 | 12 | 12 | 51
SDC - Sonoma | 108 | 424 | 1 | 0 | 60 | 236 | 5 | 17 | 42 | 168
TOTAL | 201 | 819 | 18 | 8 | 88 | 368 | 12 | 45 | 75 | 318
Change in number of projects from prior month | 0 |  | -6 | +2 | +3 |  | -1 |  | +2
Source: DDS analysis of Regional Center information provided as October 31, 2017. Status reports may lag status changes by 30 to 60 days.
Notes: Completed and in-progress homes developed outside the Community Placement Plan (CPP) process and CPP homes developed prior to the announcement of
Developmental Center (DC) closure may have additional capacity for DC consumers. Additional capacity in some homes has been encumbered for consumers in the
community. Includes 9 Supported Living Services (SLS) projects, which do not have a specific capacity.
1 All currently active start-up projects related to DC closure.
2 Projects have been approved and are in the Request for Proposals process or actively searching for a property/site.
3 Properties are in escrow to purchase a residential development.
4 Properties have been acquired and are undergoing renovation/rehabilitation.
5 Properties have completed renovation/rehabilitation and are in the process of obtaining a license, vendor and/or certification.
6 Properties are completed and currently serving or able to serve consumers.
TABLE 1B: FAIRVIEW DEVELOPMENTAL CENTER
Regional Center | Total Approved Start-Up Projects 1 |  | Number of Projects in Each Stage of Development
|  |  | Pre-Acquisition 2 | In Escrow 3 | Acquired and Under Renovation 4 |  | Pending Licensure 5 |  | Licensed, Vendored and Certified 6
| Projects | Capacity | Projects | Projects | Projects | Capacity | Projects | Capacity | Projects | Capacity
ELARC - Eastern Los Angeles County | 3 | 24 | 0 | 0 | 0 | 0 | 1 | 4 | 2 | 20
HRC - Harbor | 10 | 27 | 1 | 0 | 3 | 9 | 0 | 0 | 6 | 23
NLACRC - North Los Angeles County | 6 | 19 | 0 | 0 | 0 | 0 | 1 | 4 | 5 | 25
RCOC - Orange County | 20 | 90 | 8 | 3 | 7 | 32 | 1 | 4 | 1 | 4
SCLARC - South Central Los Angeles | 5 | 16 | 0 | 0 | 3 | 12 | 0 | 0 | 2 | 7
SDRC - San Diego | 9 | 39 | 2 | 1 | 4 | 18 | 0 | 0 | 2 | 8
SGPRC - San Gabriel/Pomona | 6 | 26 | 1 | 1 | 0 | 0 | 1 | 4 | 3 | 12
TOTAL | 59 | 241 | 12 | 5 | 17 | 71 | 4 | 16 | 21 | 99
Change in number of projects from prior month | 0 |  | -3 | +1 | +2 |  | 0 |  | 0
Source: DDS analysis of Regional Center information provided as October 31, 2017. Status reports may lag status changes by 30 to 60 days.
Notes: Completed and in-progress homes developed outside the Community Placement Plan (CPP) process and CPP homes developed prior to the announcement of
Developmental Center (DC) closure may have additional capacity for DC consumers. Additional capacity in some homes has been encumbered for consumers in the
community. Includes 3 Supported Living Services (SLS) projects, which do not have a specific capacity.
1 All currently active start-up projects related to DC closure.
2 Projects have been approved and are in the Request for Proposals process or actively searching for a property/site.
3 Properties are in escrow to purchase a residential development.
4 Properties have been acquired and are undergoing renovation/rehabilitation.
5 Properties have completed renovation/rehabilitation and are in the process of obtaining a license, vendor and/or certification.
6 Properties are completed and currently serving or able to serve consumers.
TABLE 1C: PORTERVILLE DEVELOPMENTAL CENTER
Regional Center | Total Approved Start-Up Projects 1 |  | Number of Projects in Each Stage of Development
|  |  | Pre-Acquisition 2 | In Escrow 3 | Acquired and Under Renovation 4 |  | Pending Licensure 5 |  | Licensed, Vendored and Certified 6
| Projects | Capacity | Projects | Projects | Projects | Capacity | Projects | Capacity | Projects | Capacity
CVRC - Central Valley | 14 | 55 | 1 | 3 | 2 | 9 | 2 | 8 | 6 | 25
KRC - Kern | 11 | 46 | 4 | 0 | 4 | 17 | 0 | 0 | 3 | 12
TCRC - Tri-Counties | 7 | 32 | 0 | 0 | 4 | 20 | 1 | 4 | 2 | 8
VMRC - Valley Mountain | 2 | 21 | 0 | 0 | 1 | 15 | 0 | 0 | 1 | 6
TOTAL | 34 | 154 | 5 | 3 | 11 | 61 | 3 | 12 | 12 | 51
Change in number of projects from prior month | 0 |  | -3 | +1 | +1 |  | 0 |  | +1
Source: DDS analysis of Regional Center information provided as October 31, 2017. Status reports may lag status changes by 30 to 60 days.
Notes: Completed and in-progress homes developed outside the Community Placement Plan (CPP) process and CPP homes developed prior to the announcement of
Developmental Center (DC) closure may have additional capacity for DC consumers. Additional capacity in some homes has been encumbered for consumers in the
community.
1 All currently active start-up projects related to DC closure.
2 Projects have been approved and are in the Request for Proposals process or actively searching for a property/site.
3 Properties are in escrow to purchase a residential development.
4 Properties have been acquired and are undergoing renovation/rehabilitation.
5 Properties have completed renovation/rehabilitation and are in the process of obtaining a license, vendor and/or certification.
6 Properties are completed and currently serving or able to serve consumers.
TABLE 1D: SONOMA DEVELOPMENTAL CENTER
Regional Center | Total Approved Start-Up Projects 1 |  | Number of Projects in Each Stage of Development
|  |  | Pre-Acquisition 2 | In Escrow 3 | Acquired and Under Renovation 4 |  | Pending Licensure 5 |  | Licensed, Vendored and Certified 6
| Projects | Capacity | Projects | Projects | Projects | Capacity | Projects | Capacity | Projects | Capacity
ACRC - Alta California | 19 | 71 | 0 | 0 | 7 | 20 | 1 | 4 | 11 | 43
FNRC - Far Northern | 7 | 22 | 0 | 0 | 4 | 18 | 0 | 0 | 3 | 9
GGRC - Golden Gate | 23 | 92 | 1 | 0 | 11 | 44 | 0 | 0 | 11 | 44
NBRC - North Bay | 31 | 128 | 0 | 0 | 19 | 80 | 2 | 5 | 10 | 43
RCEB - East Bay | 26 | 103 | 0 | 0 | 17 | 66 | 2 | 8 | 7 | 29
SARC - San Andreas | 2 | 8 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0
TOTAL | 108 | 424 | 1 | 0 | 60 | 236 | 5 | 17 | 42 | 168
Change in number of projects from prior month | 0 |  | 0 | 0 | 0 |  | -1 |  | +1
Source: DDS analysis of Regional Center information provided as October 31, 2017. Status reports may lag status changes by 30 to 60 days.
Notes: Completed and in-progress homes developed outside the Community Placement Plan (CPP) process and CPP homes developed prior to the announcement of
Developmental Center (DC) closure may have additional capacity for DC consumers. Additional capacity in some homes has been encumbered for consumers in the
community. Includes 6 Supported Living Services (SLS) projects, which do not have a specific capacity.
1 All currently active start-up projects related to DC closure.
2 Projects have been approved and are in the Request for Proposals process or actively searching for a property/site.
3 Properties are in escrow to purchase a residential development.
4 Properties have been acquired and are undergoing renovation/rehabilitation.
5 Properties have completed renovation/rehabilitation and are in the process of obtaining a license, vendor and/or certification.
6 Properties are completed and currently serving or able to serve consumers.
EXPORT REPORT
RUN REPORT
CLEAR REPORT