## Transitions
NUMBER OF CONSUMERS TRANSITIONING INTO THE COMMUNITY FROM DEVELOPMENTAL CENTERS SUBJECT TO CLOSURE PROJECTED AND ACTUAL TRANSITIONS
April 2017 projected and actual; May 2017 projected
Transitions are projected for individual consumers based on scheduled or projected transition review meetings.
TABLE 2A: ALL DEVELOPMENTAL CENTERS
Developmental Center | Fiscal Year 2016-17 |  |  | April 2017 |  | May 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through April 2017 | Remaining Transitions | Projected | Actual | Projected
FDC - Fairview | 81 | 36 | 45 | 2 | 2 | 6
PDC - Porterville | 34 | 23 | 11 | 2 | 2 | 0
SDC - Sonoma | 84 | 59 | 25 | 9 | 7 | 9
TOTAL | 199 | 118 | 81 | 13 | 11 | 15
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers and the secure treatment program.
TABLE 2B: FAIRVIEW DEVELOPMENTAL CENTER
In Fiscal Year 2016-17 through April 2017, 36 consumers have transitioned from Fairview Developmental Center (FDC) to the community.
In April 2017, 2 consumers from FDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 2 consumers from FDC would transition to the community in April 2017.
Regional Center | Fiscal Year 2016-17 |  |  | April 2017 |  | May 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through April 2017 | Remaining Transitions | Projected | Actual | Projected
ELARC - Eastern Los Angeles | 9 | 2 | 7 | 1 | 1 | 1
FDLRC - Frank D. Lanterman | 4 | 0 | 4 | 0 | 0 | 0
HRC - Harbor | 7 | 4 | 3 | 0 | 0 | 0
IRC - Inland | 2 | 2 | 0 | 1 | 1 | 1
KRC - Kern | 0 | 0 | 0 | 0 | 0 | 0
NLACRC - North Los Angeles County | 10 | 8 | 2 | 0 | 0 | 0
RCOC - Orange County | 13 | 8 | 5 | 0 | 0 | 0
SARC - San Andreas | 1 | 0 | 1 | 0 | 0 | 1
SCLARC - South Central Los Angeles | 3 | 5 | -2 | 0 | 0 | 1
SDRC - San Diego | 16 | 2 | 14 | 0 | 0 | 2
SGPRC - San Gabriel/Pomona | 7 | 4 | 3 | 0 | 0 | 0
TCRC - Tri-Counties | 4 | 1 | 3 | 0 | 0 | 0
VMRC - Valley Mountain | 5 | 0 | 5 | 0 | 0 | 0
TOTAL | 81 | 36 | 45 | 2 | 2 | 6
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in the acute crisis center.
TABLE 2C: PORTERVILLE DEVELOPMENTAL CENTER
In Fiscal Year 2016-17 through April 2017, 23 consumers have transitioned from Porterville Developmental Center (PDC) to the community.
In April 2017, 2 consumers from PDC's General Treatment Area transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 2 consumers from FDC would transition to the community in April 2017.
Regional Center | Fiscal Year 2016-17 |  |  | April 2017 |  | May 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through April 2017 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 2 | 0 | 2 | 0 | 0 | 0
CVRC - Central Valley | 17 | 11 | 6 | 1 | 1 | 0
FDLRC - Frank D. Lanterman | 1 | 0 | 1 | 0 | 0 | 0
FNRC - Far Northern | 2 | 0 | 2 | 0 | 0 | 0
GGRC - Golden Gate | 1 | 1 | 0 | 0 | 0 | 0
IRC - Inland | 1 | 0 | 1 | 0 | 0 | 0
KRC - Kern | 7 | 9 | -2 | 0 | 0 | 0
NLACRC - North Los Angeles County | 0 | 1 | -1 | 0 | 0 | 0
TCRC - Tri-Counties | 0 | 1 | -1 | 1 | 1 | 0
VMRC - Valley Mountain | 3 | 0 | 3 | 0 | 0 | 0
TOTAL | 34 | 23 | 11 | 2 | 2 | 0
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Notes: Excludes consumers in the secure treatment program. ( ) indicates that total transitions exceed the CPP projection.
TABLE 2D: SONOMA DEVELOPMENTAL CENTER
In Fiscal Year 2016-17 through April 2017, 59 consumers have transitioned from Sonoma Developmental Center (SDC) to the community.
In April 2017, 7 consumers from SDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 9 consumers from SDC would transition to the community in April 2017. Two projected placements were delayed because of health issues.
Regional Center | Fiscal Year 2016-17 |  |  | April 2017 |  | May 2017
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through April 2017 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 17 | 10 | 7 | 3 | 3 | 4
FNRC - Far Northern | 2 | 3 | -1 | 0 | 0 | 0
GGRC - Golden Gate | 20 | 12 | 8 | 1 | 0 | 2
NBRC - North Bay | 22 | 16 | 6 | 3 | 2 | 1
RCEB - East Bay | 19 | 11 | 8 | 1 | 1 | 2
RCRC - Redwood Coast | 1 | 2 | -1 | 1 | 1 | 0
SARC - San Andreas | 0 | 1 | -1 | 0 | 0 | 0
SDRC - San Diego | 0 | 1 | -1 | 0 | 0 | 0
TCRC - Tri-Counties | 2 | 3 | -1 | 0 | 0 | 0
VMRC - Valley Mountain | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 84 | 59 | 25 | 9 | 7 | 9
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Notes: Excludes consumers in the acute crisis center. ( ) indicates that total transitions exceed the CPP projection.