## Feb 2018 -DRAFT
NUMBER OF CONSUMERS TRANSITIONING INTO THE COMMUNITY FROM DEVELOPMENTAL CENTERS SUBJECT TO CLOSURE PROJECTED AND ACTUAL TRANSITIONS
February 2018 projected and actual; March 2018 projected
Transitions are projected for individual consumers based on scheduled or projected transition review meetings.
TABLE 2A: ALL DEVELOPMENTAL CENTERS
Developmental Center | Fiscal Year 2017-18 |  |  | February 2018 |  | March 2018
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through February 2018 | Remaining Transitions 1 | Projected | Actual | Projected
FDC - Fairview 1 | 95 | 28 | 68 | 5 | 2 | 6
PDC - Porterville | 32 | 32 | 0 | 2 | 3 | 5
SDC - Sonoma | 184 | 101 | 83 | 17 | 14 | 16
TOTAL 1 | 311 | 161 | 151 | 24 | 19 | 27
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers and the secure treatment program.
1 Includes a consumer placed from FDLRC who later returned to FDC and needs a new community placement.
TABLE 2B: FAIRVIEW DEVELOPMENTAL CENTER
In Fiscal Year 2017-18 through February 2018, 28 consumers have transitioned from Fairview Developmental Center (FDC) to the community.
In February 2018, 2 consumers from FDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 5 consumers from FDC would transition to the community in February 2018. The projected placements that did not occur this month were due to three consumers' need for a longer transition process.
Regional Center | Fiscal Year 2017-18 |  |  | February 2018 |  | March 2018
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through February 2018 | Remaining Transitions 1 | Projected | Actual | Projected
ACRC - Alta California | 1 | 1 | 0 | 0 | 0 | 0
ELARC - Eastern Los Angeles | 5 | 0 | 5 | 0 | 0 | 1
FDLRC - Frank D. Lanterman 1 | 2 | 0 | 3 | 0 | 0 | 0
GGRC - Golden Gate | 0 | 0 | 0 | 0 | 0 | 0
HRC - Harbor | 3 | 3 | 0 | 1 | 1 | 0
IRC - Inland | 4 | 1 | 3 | 0 | 0 | 0
NLACRC - North Los Angeles County | 6 | 3 | 3 | 0 | 0 | 0
RCEB - East Bay | 0 | 0 | 0 | 0 | 0 | 0
RCOC - Orange County | 35 | 2 | 33 | 2 | 0 | 4
SARC - San Andreas | 1 | 0 | 1 | 0 | 0 | 0
SCLARC - South Central Los Angeles | 7 | 5 | 2 | 0 | 0 | 1
SDRC - San Diego | 15 | 5 | 10 | 2 | 1 | 0
SGPRC - San Gabriel/Pomona | 5 | 3 | 2 | 0 | 0 | 0
TCRC - Tri-Counties | 5 | 0 | 5 | 0 | 0 | 0
WRC - Westside | 6 | 5 | 1 | 0 | 0 | 0
TOTAL 1 | 95 | 28 | 68 | 5 | 2 | 6
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in the acute crisis center.
1 Includes a consumer placed from FDLRC who later returned to FDC and needs a new community placement.
TABLE 2C: PORTERVILLE DEVELOPMENTAL CENTER
In Fiscal Year 2017-18 through February 2018, 32 consumers have transitioned from Porterville Developmental Center (PDC) to the community.
In February 2018, 3 consumers from PDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 2 consumers from PDC would transition to the community in February 2018.
Regional Center | Fiscal Year 2017-18 |  |  | February 2018 |  | March 2018
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through February 2018 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 1 | 3 | -2 | 0 | 0 | 1
CVRC - Central Valley | 10 | 20 | -10 | 1 | 3 | 2
ELARC - Eastern Los Angeles | 0 | 1 | -1 | 0 | 0 | 0
FDLRC - Frank D Lanterman | 0 | 1 | -1 | 0 | 0 | 0
FNRC - Far Northern | 1 | 0 | 1 | 0 | 0 | 0
GGRC - Golden Gate | 0 | 0 | 0 | 0 | 0 | 2
IRC - Inland | 1 | 0 | 1 | 0 | 0 | 0
KRC - Kern | 7 | 3 | 4 | 0 | 0 | 0
NLACRC - North Los Angeles County | 1 | 0 | 1 | 0 | 0 | 0
RCEB - East Bay | 0 | 0 | 0 | 0 | 0 | 0
RCRC - Redwood Coast | 1 | 0 | 1 | 0 | 0 | 0
SARC - San Andreas | 2 | 0 | 2 | 0 | 0 | 0
SCLARC - South Central Los Angeles | 3 | 0 | 3 | 0 | 0 | 0
SDRC - San Diego | 0 | 0 | 0 | 0 | 0 | 0
SGPRC - San Gabriel/Pomona | 0 | 0 | 0 | 0 | 0 | 0
TCRC - Tri-Counties | 1 | 2 | -1 | 0 | 0 | 0
VMRC - Valley Mountain | 3 | 2 | 1 | 1 | 0 | 0
WRC - Westside | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 32 | 32 | 0 | 2 | 3 | 5
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Notes: Excludes consumers in the secure treatment program. ( ) indicates that total transitions exceed the CPP projection.
TABLE 2D: SONOMA DEVELOPMENTAL CENTER
In Fiscal Year 2017-18 through February 2018, 101 consumers have transitioned from Sonoma Developmental Center (SDC) to the community.
In February 2018, 14 consumers from SDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 17 consumers from SDC would transition to the community in February 2018. The projected placements that did not occur this month were due to three consumers' need for a longer transition process, the completion of a home, or health issues.
Regional Center | Fiscal Year 2017-18 |  |  | February 2018 |  | March 2018
| Approved Community Placement Plan (CPP) Transitions | Total Transitions Through February 2018 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 27 | 21 | 6 | 4 | 2 | 5
CVRC - Central Valley | 2 | 2 | 0 | 0 | 0 | 0
FNRC - Far Northern | 4 | 4 | 0 | 1 | 1 | 0
GGRC - Golden Gate | 30 | 28 | 2 | 3 | 4 | 4
NBRC - North Bay | 57 | 14 | 43 | 4 | 5 | 4
RCEB - East Bay | 58 | 29 | 29 | 5 | 2 | 3
RCRC - Redwood Coast | 2 | 0 | 2 | 0 | 0 | 0
SARC - San Andreas | 3 | 3 | 0 | 0 | 0 | 0
TCRC - Tri-Counties | 0 | 0 | 0 | 0 | 0 | 0
VMRC - Valley Mountain | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 184 | 101 | 83 | 17 | 14 | 16
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Notes: Excludes consumers in the acute crisis center.