## September 2018 -DRAFT
NUMBER OF CONSUMERS TRANSITIONING INTO THE COMMUNITY FROM DEVELOPMENTAL CENTERS SUBJECT TO CLOSURE PROJECTED AND ACTUAL TRANSITIONS
September 2018 projected and actual; October 2018 projected.
Transitions are projected for individual consumers based on scheduled or projected transition review meetings.
TABLE 2A: ALL DEVELOPMENTAL CENTERS
Developmental Center | Fiscal Year 2018-19 |  |  | September 2018 |  | October 2018
| Projected Placements as of May 2018 | Total Transitions Through September 2018 | Remaining Transitions | Projected | Actual | Projected
FDC - Fairview | 83 | 9 | 74 | 5 | 4 | 4
PDC - Porterville | 55 | 5 | 50 | 2 | 0 | 4
SDC - Sonoma | 83 | 36 | 47 | 15 | 8 | 20
TOTAL | 221 | 50 | 171 | 22 | 12 | 28
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers and the secure treatment program.
TABLE 2B: FAIRVIEW DEVELOPMENTAL CENTER
In Fiscal Year 2018-19 through September 2018, 9 consumer has transitioned from Fairview Developmental Center (FDC) to the community.
In September 2018, 4 consumers from FDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 5 consumers from FDC would transition to the community in September 2018. The projected placement that did not occur this month was due to a consumer's need for a longer transition process.
Regional Center | Fiscal Year 2018-19 |  |  | September 2018 |  | October 2018
| Projected Placements as of May 20181 | Total Transitions Through September 2018 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | -- | 0 | -- | 0 | 0 | 0
ELARC - Eastern Los Angeles | -- | 0 | -- | 0 | 0 | 1
FDLRC - Frank D. Lanterman | -- | 0 | -- | 0 | 0 | 0
GGRC - Golden Gate | -- | 0 | -- | 0 | 0 | 0
HRC - Harbor | -- | 1 | -- | 0 | 0 | 0
IRC - Inland | -- | 0 | -- | 0 | 0 | 0
NLACRC - North Los Angeles County | -- | 1 | -- | 0 | 0 | 0
RCEB - East Bay | -- | 1 | -- | 1 | 1 | 0
RCOC - Orange County | -- | 2 | -- | 2 | 2 | 0
SARC - San Andreas | -- | 0 | -- | 0 | 0 | 0
SCLARC - South Central Los Angeles | -- | 0 | -- | 1 | 0 | 1
SDRC - San Diego | -- | 2 | -- | 0 | 0 | 1
SGPRC - San Gabriel/Pomona | -- | 1 | -- | 1 | 1 | 1
TCRC - Tri-Counties | -- | 0 | -- | 0 | 0 | 0
WRC - Westside | -- | 1 | -- | 0 | 0 | 0
TOTAL | 83 | 9 | 74 | 5 | 4 | 4
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers.
1 Placement projections are not available for individual RCs.
TABLE 2C: PORTERVILLE DEVELOPMENTAL CENTER
In Fiscal Year 2018-19 through September 2018, 5 consumers have transitioned from Porterville Developmental Center (PDC) to the community.
In September 2018, 0 consumers from PDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 2 consumers from PDC would transition to the community in September 2018. The projected placements that did not occur this month were due to the delay of a home being ready.
Regional Center | Fiscal Year 2018-19 |  |  | September 2018 |  | October 2018
| Projected Placements as of May 20181 | Total Transitions Through September 2018 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | -- | 1 | -- | 0 | 0 | 0
CVRC - Central Valley | -- | 1 | -- | 0 | 0 | 1
ELARC - Eastern Los Angeles | -- | 0 | -- | 0 | 0 | 0
FDLRC - Frank D Lanterman | -- | 0 | -- | 0 | 0 | 0
FNRC - Far Northern | -- | 0 | -- | 0 | 0 | 0
GGRC - Golden Gate | -- | 0 | -- | 0 | 0 | 0
IRC - Inland | -- | 0 | -- | 0 | 0 | 0
KRC - Kern | -- | 2 | -- | 0 | 0 | 0
NLACRC - North Los Angeles County | -- | 0 | -- | 0 | 0 | 1
RCEB - East Bay | -- | 0 | -- | 0 | 0 | 0
RCRC - Redwood Coast | -- | 0 | -- | 0 | 0 | 0
SARC - San Andreas | -- | 0 | -- | 0 | 0 | 0
SCLARC - South Central Los Angeles | -- | 0 | -- | 2 | 0 | 2
SDRC - San Diego | -- | 0 | -- | 0 | 0 | 0
SGPRC - San Gabriel/Pomona | -- | 0 | -- | 0 | 0 | 0
TCRC - Tri-Counties | -- | 1 | -- | 0 | 0 | 0
VMRC - Valley Mountain | -- | 0 | -- | 0 | 0 | 0
WRC - Westside | -- | 0 | -- | 0 | 0 | 0
TOTAL | 55 | 5 | 50 | 2 | 0 | 4
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in the secure treatment program.
1 Placement projections are not available for individual RCs.
TABLE 2D: SONOMA DEVELOPMENTAL CENTER
In Fiscal Year 2018-19 through September 2018, 36 consumers have transitioned from Sonoma Developmental Center (SDC) to the community.
In September 2018, 8 consumers from SDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 15 consumers from SDC would transition to the community in September 2018. The projected placements that did not occur this month were due to the delay of homes being ready and consumers needing further home visits.
Regional Center | Fiscal Year 2018-19 |  |  | September 2018 |  | October 2018
| Projected Placements as of May 20181 | Total Transitions Through September 2018 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | -- | 1 | -- | 0 | 0 | 0
CVRC - Central Valley | -- | 0 | -- | 0 | 0 | 0
FNRC - Far Northern | -- | 0 | -- | 0 | 0 | 0
GGRC - Golden Gate | -- | 8 | -- | 3 | 2 | 1
NBRC - North Bay | -- | 19 | -- | 9 | 5 | 10
RCEB - East Bay | -- | 8 | -- | 3 | 1 | 9
RCRC - Redwood Coast | -- | 0 | -- | 0 | 0 | 0
SARC - San Andreas | -- | 0 | -- | 0 | 0 | 0
TCRC - Tri-Counties | -- | 0 | -- | 0 | 0 | 0
VMRC - Valley Mountain | -- | 0 | -- | 0 | 0 | 0
TOTAL | 83 | 36 | 47 | 15 | 8 | 20
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers.
1 Placement projections are not available for individual RCs.