## April 2019
NUMBER OF CONSUMERS TRANSITIONING INTO THE COMMUNITY FROM DEVELOPMENTAL CENTERS SUBJECT TO CLOSURE PROJECTED AND ACTUAL TRANSITIONS
April 2019 projected and actual; May 2019 projected.
Transitions are projected for individual consumers based on scheduled or projected transition review meetings.
TABLE 2A: ALL DEVELOPMENTAL CENTERS
Developmental Center | Fiscal Year 2018-19 |  |  | April 2019 |  | May 2019
| Projected Placements as of May 2018 | Total Transitions Through April 2019 | Remaining Transitions1 | Projected | Actual | Projected
FDC - Fairview | 83 | 49 | 34 | 17 | 13 | 9
PDC - Porterville | 55 | 14 | 41 | 1 | 1 | 4
SDC - Sonoma1 | 83 | 75 | 0 | 0 | 0 | 0
TOTAL | 221 | 138 | 75 | 18 | 14 | 13
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers and the secure treatment program.
1 As of 12/31/18, there are no remaining individuals at Sonoma Developmental Center to be placed.
TABLE 2B: FAIRVIEW DEVELOPMENTAL CENTER
In Fiscal Year 2018-19 through April 2019, 49 consumers have transitioned from Fairview Developmental Center (FDC) to the community.
In April 2019, 13 consumers from FDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 17 consumers from FDC would transition to the community in April 2019. The projected placements that did not occur this month were due the need for extra time in the case of three individuals, and the delay of a home being ready in the final instance.
Regional Center | Fiscal Year 2018-19 |  |  | April 2019 |  | May 2019
| Projected Placements as of May 20181 | Total Transitions Through April 2019 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | -- | 0 | -- | 0 | 0 | 1
ELARC - Eastern Los Angeles | -- | 1 | -- | 0 | 0 | 0
FDLRC - Frank D. Lanterman | -- | 0 | -- | 0 | 0 | 0
GGRC - Golden Gate | -- | 1 | -- | 0 | 0 | 0
HRC - Harbor | -- | 1 | -- | 0 | 0 | 0
IRC - Inland | -- | 0 | -- | 0 | 0 | 0
KRC - Kern | -- | 0 | -- | 0 | 0 | 1
NLACRC - North Los Angeles County | -- | 1 | -- | 0 | 0 | 0
RCEB - East Bay | -- | 1 | -- | 0 | 0 | 0
RCOC - Orange County | -- | 35 | -- | 17 | 13 | 6
SCLARC - South Central Los Angeles | -- | 1 | -- | 0 | 0 | 0
SDRC - San Diego | -- | 3 | -- | 0 | 0 | 0
SGPRC - San Gabriel/Pomona | -- | 2 | -- | 0 | 0 | 0
TCRC - Tri-Counties | -- | 1 | -- | 0 | 0 | 1
WRC - Westside | -- | 2 | -- | 0 | 0 | 0
TOTAL | 83 | 49 | 34 | 17 | 13 | 9
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers.
1 Placement projections are not available for individual RCs.
TABLE 2C: PORTERVILLE DEVELOPMENTAL CENTER
In Fiscal Year 2018-19 through April 2019, 14 consumers have transitioned from Porterville Developmental Center (PDC) to the community.
In April 2019, 1 consumer from PDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 1 consumer from PDC would transition to the community in April 2019.
Regional Center | Fiscal Year 2018-19 |  |  | April 2019 |  | May 2019
| Projected Placements as of May 20181 | Total Transitions Through April 2019 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | -- | 1 | -- | 0 | 0 | 3
CVRC - Central Valley | -- | 4 | -- | 1 | 1 | 0
ELARC - Eastern Los Angeles | -- | 0 | -- | 0 | 0 | 0
FDLRC - Frank D Lanterman | -- | 0 | -- | 0 | 0 | 0
FNRC - Far Northern | -- | 0 | -- | 0 | 0 | 1
GGRC - Golden Gate | -- | 0 | -- | 0 | 0 | 0
IRC - Inland | -- | 0 | -- | 0 | 0 | 0
KRC - Kern | -- | 3 | -- | 0 | 0 | 0
NLACRC - North Los Angeles County | -- | 1 | -- | 0 | 0 | 0
RCEB - East Bay | -- | 0 | -- | 0 | 0 | 0
RCRC - Redwood Coast | -- | 0 | -- | 0 | 0 | 0
SARC - San Andreas | -- | 1 | -- | 0 | 0 | 0
SCLARC - South Central Los Angeles | -- | 2 | -- | 0 | 0 | 0
SDRC - San Diego | -- | 0 | -- | 0 | 0 | 0
SGPRC - San Gabriel/Pomona | -- | 1 | -- | 0 | 0 | 0
TCRC - Tri-Counties | -- | 1 | -- | 0 | 0 | 0
VMRC - Valley Mountain | -- | 0 | -- | 0 | 0 | 0
WRC - Westside | -- | 0 | -- | 0 | 0 | 0
TOTAL | 55 | 14 | 41 | 1 | 1 | 4
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in the secure treatment program.
1 Placement projections are not available for individual RCs.
TABLE 2D: SONOMA DEVELOPMENTAL CENTER
#REF!
As of 12/31/18, there were no remaining individuals living at Sonoma Developmental Center.
Regional Center | Fiscal Year 2018-19 |  |  | #REF! |  | #REF!
| Projected Placements as of May 20181 | #REF! | Remaining Transitions2 | Projected | Actual | Projected
ACRC - Alta California | -- | 1 | -- | 0
CVRC - Central Valley | -- | 0 | -- | 0
FNRC - Far Northern | -- | 0 | -- | 0
GGRC - Golden Gate | -- | 9 | -- | 0
NBRC - North Bay | -- | 36 | -- | 0
RCEB - East Bay | -- | 28 | -- | 0
RCRC - Redwood Coast | -- | 1 | -- | 0
SARC - San Andreas | -- | 0 | -- | 0
TCRC - Tri-Counties | -- | 0 | -- | 0
VMRC - Valley Mountain | -- | 0 | -- | 0
TOTAL | 83 | 75 | 0 | 0 | 0 | 0