## Jul 2019 to post
NUMBER OF CONSUMERS TRANSITIONING INTO THE COMMUNITY FROM DEVELOPMENTAL CENTERS SUBJECT TO CLOSURE PROJECTED AND ACTUAL TRANSITIONS
July 2019 projected and actual; August 2019 projected.
Transitions are projected for individual consumers based on scheduled or projected transition review meetings.
TABLE 2A: ALL DEVELOPMENTAL CENTERS
Developmental Center | Fiscal Year 2019-20 |  |  | July 2019 |  | August 2019
| Projected Placements as of June 2019 | Total Transitions Through July 2019 | Remaining Transitions | Projected | Actual | Projected
FDC - Fairview | 43 | 8 | 35 | 9 | 8 | 2
PDC - Porterville | 34 | 5 | 29 | 7 | 5 | 12
TOTAL | 77 | 13 | 64 | 16 | 13 | 14
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers and the secure treatment program.
TABLE 2B: FAIRVIEW DEVELOPMENTAL CENTER
In Fiscal Year 2019-20 through July 2019, 8 consumers have transitioned from Fairview Developmental Center (FDC) to the community.
In July 2019, 8 consumers from FDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 9 consumers from FDC would transition to the community in July 2019. The projected placement that did not occur this month was due to extra time needed to determine one individual's proper level of care.
Regional Center | Fiscal Year 2019-20 |  |  | July 2019 |  | August 2019
| Projected Placements as of June 2019 | Total Transitions Through July 2019 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 1 | 0 | 1 | 0 | 0 | 0
ELARC - Eastern Los Angeles | 2 | 0 | 2 | 0 | 0 | 0
GGRC - Golden Gate | 1 | 0 | 1 | 0 | 0 | 0
IRC - Inland | 1 | 0 | 1 | 0 | 0 | 0
KRC - Kern | 1 | 1 | 0 | 1 | 1 | 0
NLACRC - North Los Angeles County | 1 | 0 | 1 | 0 | 0 | 0
RCEB - East Bay | 1 | 0 | 1 | 0 | 0 | 0
RCOC - Orange County | 15 | 5 | 10 | 6 | 5 | 2
SDRC - San Diego | 18 | 2 | 16 | 2 | 2 | 0
TCRC - Tri-Counties | 1 | 0 | 1 | 0 | 0 | 0
WRC - Westside | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 43 | 8 | 35 | 9 | 8 | 2
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers.
TABLE 2C: PORTERVILLE DEVELOPMENTAL CENTER
In Fiscal Year 2019-20 through July 2019, 5 consumers have transitioned from Porterville Developmental Center (PDC) to the community.
In July 2019, 5 consumers from PDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 7 consumers from PDC would transition to the community in July 2019. The projected placements that did not occur this month were due to staff not being ready in one case, and an individual not being ready in the other case.
Regional Center | Fiscal Year 2019-20 |  |  | July 2019 |  | August 2019
| Projected Placements as of June 2019 | Total Transitions Through July 2019 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 2 | 0 | 2 | 0 | 0 | 1
CVRC - Central Valley | 13 | 3 | 10 | 4 | 3 | 5
GGRC - Golden Gate | 1 | 0 | 1 | 0 | 0 | 0
KRC - Kern | 7 | 0 | 7 | 0 | 0 | 3
RCEB - East Bay | 1 | 0 | 1 | 0 | 0 | 0
SCLARC - South Central Los Angeles | 1 | 0 | 1 | 0 | 0 | 0
SDRC - San Diego | 1 | 0 | 1 | 0 | 0 | 0
TCRC - Tri-Counties | 7 | 2 | 5 | 3 | 2 | 3
VMRC - Valley Mountain | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 34 | 5 | 29 | 7 | 5 | 12
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in the secure treatment program.