## October 2019
NUMBER OF CONSUMERS TRANSITIONING INTO THE COMMUNITY FROM DEVELOPMENTAL CENTERS SUBJECT TO CLOSURE PROJECTED AND ACTUAL TRANSITIONS
October 2019 projected and actual; November 2019 projected.
Transitions are projected for individual consumers based on scheduled or projected transition review meetings.
TABLE 2A: ALL DEVELOPMENTAL CENTERS
Developmental Center | Fiscal Year 2019-20 |  |  | October 2019 |  | November 2019
| Projected Placements as of June 2019 | Total Transitions Through October 2019 | Remaining Transitions | Projected | Actual | Projected
FDC - Fairview | 43 | 21 | 22 | 15 | 8 | 10
PDC - Porterville | 34 | 24 | 10 | 9 | 4 | 4
TOTAL | 77 | 45 | 32 | 24 | 12 | 14
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers and the secure treatment program.
TABLE 2B: FAIRVIEW DEVELOPMENTAL CENTER
In Fiscal Year 2019-20 through October 2019, 21 consumers have transitioned from Fairview Developmental Center (FDC) to the community.
In October 2019, 8 consumers from FDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 15 consumers from FDC would transition to the community in October 2019. The projected placements that did not occur this month were due to consumer health-related issues in two cases, and the delay of homes being ready for 6 other individuals.
Regional Center | Fiscal Year 2019-20 |  |  | October 2019 |  | November 2019
| Projected Placements as of June 2019 | Total Transitions Through October 2019 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 1 | 1 | 0 | 1 | 1 | 0
ELARC - Eastern Los Angeles | 2 | 0 | 2 | 0 | 0 | 0
GGRC - Golden Gate | 1 | 1 | 0 | 1 | 1 | 0
IRC - Inland | 1 | 1 | 0 | 0 | 1 | 0
KRC - Kern | 1 | 1 | 0 | 0 | 0 | 0
NLACRC - North Los Angeles County | 1 | 0 | 1 | 0 | 0 | 0
RCEB - East Bay | 1 | 0 | 1 | 0 | 0 | 1
RCOC - Orange County | 15 | 8 | 7 | 5 | 1 | 5
SDRC - San Diego | 18 | 9 | 9 | 8 | 4 | 4
TCRC - Tri-Counties | 1 | 0 | 1 | 0 | 0 | 0
WRC - Westside | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 43 | 21 | 22 | 15 | 8 | 10
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in acute crisis centers.
TABLE 2C: PORTERVILLE DEVELOPMENTAL CENTER
In Fiscal Year 2019-20 through October 2019, 24 consumers have transitioned from Porterville Developmental Center (PDC) to the community.
In October 2019, 4 consumers from PDC transitioned to the community. In the previous month, Regional Centers (RCs) had projected that 9 consumers from PDC would transition to the community in October 2019. The projected placements that did not occur this month were due to court requirements in one case, and homes not being ready for four other individuals.
Regional Center | Fiscal Year 2019-20 |  |  | October 2019 |  | November 2019
| Projected Placements as of June 2019 | Total Transitions Through October 2019 | Remaining Transitions | Projected | Actual | Projected
ACRC - Alta California | 2 | 2 | 0 | 0 | 0 | 0
CVRC - Central Valley | 13 | 11 | 2 | 2 | 1 | 0
GGRC - Golden Gate | 1 | 0 | 1 | 1 | 0 | 0
KRC - Kern | 7 | 5 | 2 | 4 | 2 | 2
RCEB - East Bay | 1 | 0 | 1 | 0 | 0 | 0
SCLARC - South Central Los Angeles | 1 | 0 | 1 | 0 | 0 | 1
SDRC - San Diego | 1 | 1 | 0 | 1 | 1 | 0
TCRC - Tri-Counties | 7 | 5 | 2 | 1 | 0 | 1
VMRC - Valley Mountain | 1 | 0 | 1 | 0 | 0 | 0
TOTAL | 34 | 24 | 10 | 9 | 4 | 4
Source: DDS analysis of information provided by Developmental Centers and Regional Centers.
Note: Excludes consumers in the secure treatment program.