## Start-Up (In Prog) & Placement
REGIONAL CENTER MONTHLY UPDATE IN-PROGRESS RESIDENTIAL START-UP & CONSUMER TRANSITION
FY 2022-23 CPP GUIDELINES Enclosure E | [11 empty] | CMS | UCI | CONSUMER NAME | PLANNED PLACEMENT DATE | MEET & GREET | SUCCESSFUL MEET & GREET | TPM (Transition Planning Meeting) | TRM (Transition Review Meeting) | PLACEMENT STATUS (CONSUMER MOVEMENT STATUS) | PLACEMENT DATE (CONSUMER MOVEMENT DATE) | TRANSFER STATUS | TRANSFER COMPLETE DATE | TRANSFER ORIGIONAL REGIONAL CENTER | TRANSFER RECEIVING REGIONAL CENTER
PROJECTED BEDS (Type & Count) | PROJECT ID | DEVELOPMENT TYPE | PROJECT STATUS (ACTIVITY STATUS) | HDO CATEGORY | HDO NAME | PROJECTED CAPACITY | PROPERTY NAME | PROPERTY ADDRESS | CITY | PROPERTY ZIP | SERVICE PROVIDER | PROJECTED SERVICE DATE | ACTUAL SERVICE DATE | (1) RFP POSTED DATE FOR HDO COMPLETE (2) RFP POSTED DATE FOR SERVICE PROVIDER | (1) EXECUTED CONTRACT FOR HDO (2) EXECUTED CONTRACT FOR SERVICE PROVIDER | (1) ACQUISITION CLOSE OF ESCROW ESTIMATED (2) ACQUISITION CLOSE OF ESCROW ACTUAL (3) SITE CONTROL COMPLETE (NON-HDO) | PERMIT SUBMITTED | (1) CONSTRUCTION START TARGET (2) CONSTRUCTION START COMPLETE | (1) CONSTRUCTION FINISH TARGET (2) CONSTRUCTION FINISH COMPLETE | FIRE CLEARANCE APPROVAL COMPLETE (STD 850 FORM COMPLETE) | LICENSE APP SUBMISSION COMPLETE | LICENSURE COMPLETE | (1) CERTIFICATION PACKET SUBMISSION TARGET (2) CERTIFICATION PACKET SUBMISSION COMPLETE (3) CERTIFICATION PACKET APPROVAL COMPLETE | VENDORIZATION COMPLETE | FIRST OCCUPANCY COMPLETE
NON CPP Placements
UNIDENTIFIED PLACEMENTS
EXPORT REPORT

## Start-Up Completed
REGIONAL CENTER MONTHLY UPDATE COMPLETED RESIDENTIAL & CONSUMER UTILIZATION | [11 empty] | CMS | UCI | CONSUMER NAME | PLANNED PLACEMENT DATE | MEET & GREET | SUCCESSFUL MEET & GREET | TPM (Transition Planning Meeting) | TRM (Transition Review Meeting) | PLACEMENT STATUS (CONSUMER MOVEMENT STATUS) | PLACEMENT DATE (CONSUMER MOVEMENT DATE) | TRANSFER STATUS | TRANSFER COMPLETE DATE | TRANSFER ORIGIONAL REGIONAL CENTER | TRANSFER RECEIVING REGIONAL CENTER
PROJECTED BEDS (Type & Count) | PROJECT ID | DEVELOPMENT TYPE | PROJECT STATUS (ACTIVITY STATUS) | HDO CATEGORY | HDO NAME | PROJECTED CAPACITY | PROPERTY NAME | PROPERTY ADDRESS | CITY | PROPERTY ZIP | SERVICE PROVIDER | PROJECTED SERVICE DATE | ACTUAL SERVICE DATE | (1) RFP POSTED DATE FOR HDO COMPLETE (2) RFP POSTED DATE FOR SERVICE PROVIDER | (1) EXECUTED CONTRACT FOR HDO (2) EXECUTED CONTRACT FOR SERVICE PROVIDER | (1) ACQUISITION CLOSE OF ESCROW ESTIMATED (2) ACQUISITION CLOSE OF ESCROW ACTUAL (3) SITE CONTROL COMPLETE (NON-HDO) | PERMIT SUBMITTED | (1) CONSTRUCTION START TARGET (2) CONSTRUCTION START COMPLETE | (1) CONSTRUCTION FINISH TARGET (2) CONSTRUCTION FINISH COMPLETE | FIRE CLEARANCE APPROVAL COMPLETE (STD 850 FORM COMPLETE) | LICENSE APP SUBMISSION COMPLETE | LICENSURE COMPLETE | (1) CERTIFICATION PACKET SUBMISSION TARGET (2) CERTIFICATION PACKET SUBMISSION COMPLETE (3) CERTIFICATION PACKET APPROVAL COMPLETE | VENDORIZATION COMPLETE | FIRST OCCUPANCY COMPLETE | SERVICE PROVIDER VENDOR NUMBER

## Non Residential Start -Up
REGIONAL CENTER MONTHLY UPDATE
NON RESIDENTIAL START-UP
# | PROJECT ID | DEVELOPMENT TYPE | PROJECT STATUS | HDO CATEGORY | PROJECTED CAPACITY | PROPERTY NAME | PROPERTY ADDRESS | CITY | PROPERTY ZIP | (1) SERVICE PROVIDER COMMITMENT COMPLETE (2) SERVICE PROVIDER | PROJECTED SERVICE DATE | ACTUAL SERVICE DATE | RFP COMPLETE | SITE CONTROL COMPLETE | FIRE CLEARANCE APPROVAL COMPLETE | LICENSE APP SUBMISSION COMPLETE | LICENSURE COMPLETE | VENDORIZATION COMPLETE | FIRST OCCUPANCY COMPLETE
IN-PROGRESS
COMPLETED

## IMD Transitions
REGIONAL CENTER IMD CONSUMER TRACKER
PROJECT ID | DEVELOPMENT TYPE | PROJECT STATUS (ACTIVITY STATUS) | PROJECTED SERVICE DATE | HDO OR NON-HDO | SPECIALTY AGE GROUP | PROPERTY NAME | PROPERTY ADDRESS | CITY | SERVICE PROVIDER | DE/SP? | REFERRALS FOR RSO'S ACCEPTED BY PROVIDER ( YES OR NO) | CLEAN HOME (PICA) (YES OR NO) | (1) CONSTRUCTION START TARGET (2) CONSTRUCTION START COMPLETE | (1) CONSTRUCTION FINISH TARGET (2) CONSTRUCTION FINISH COMPLETE | LICENSE APP SUBMISSION COMPLETE | VENDORIZATION COMPLETE | FIRE CLEARANCE APPROVAL SUBMITTED | FIRE CLEARANCE APPROVAL COMPLETE (STD 850 FORM COMPLETE) | (1) CERTIFICATION PACKET SUBMISSION TARGET (2) CERTIFICATION PACKET SUBMISSION COMPLETE (3) CERTIFICATION PACKET APPROVAL COMPLETE |  | LICENSURE COMPLETE
LOCATION | CONSUMER NAME | UCI | PLANNED PLACEMENT DATE | DATE OF BIRTH | AGE | CASE WORKER | PROJECTED PROJECT NUMBER | PROPOSED LIVING ARRANGEMENT (Planned Development Type) | PROVIDER | CONSUMER NEEDS DE/SP (YES OR NO) | 290 REGISTRANT (YES OR NO) | EXHIBITS PICA BX's (YES OR NO) | ADMISSSION DATE | LENGTH OF STAY (IN YEARS) | (1) Conserved (Yes or No) (2) Conservator Name | (1) Completed Initial assessment date (2) Last comprehensive assessment date | MEET & GREET | SUCCESSFUL MEET & GREET | RC NOTIFIED DRC OF ADMISSION (YES OR NO) | PLACEMENT STATUS (Consumer Movement Status) | PLACEMENT DATE (Consumer Movement Date)
IMD
IN ACTIVE TRANSITION TO A CPP LIVING ARRANGEMENT
RUNNING PROJECT DEVELOPMENT NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
IN ACTIVE TRANSITION TO A CPP LIVING ARRANGEMENT IN ANTOTHER RC'S AREA
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
IN ACTIVE TRANSITION TO A NON-CPP LIVING ARRANGEMENT
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
COMMUNITY ENVIRONMENT NOT YET IDENTIFIED
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
TRANSITIONED INTO THE COMMUNITY (Post placement reports)
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:
| CPP LIAISON NOTES: | [11 empty] | IMD LIAISON NOTES:

## State Operated Facilities
REGIONAL CENTER PDC/STP - CS CONSUMER TRACKER
PROJECT ID | DEVELOPMENT TYPE | HDO OR NON-HDO | PROJECTED SERVICE DATE | PROJECT STATUS (ACTIVITY STATUS) | SPECIALTY AGE GROUP | PROPERTY NAME | PROPERTY ADDRESS | CITY | SERVICE PROVIDER | DE/SP? | REFERRALS FOR RSO'S ACCEPTED BY PROVIDER ( YES OR NO) | CLEAN HOME (PICA) (YES OR NO) | (1) CONSTRUCTION START TARGET (2) CONSTRUCTION START COMPLETE | (1) CONSTRUCTION FINISH TARGET (2) CONSTRUCTION FINISH COMPLETE | LICENSE APP SUBMISSION COMPLETE | VENDORIZATION COMPLETE | FIRE CLEARANCE APPROVAL SUBMITTED | FIRE CLEARANCE APPROVAL COMPLETE (STD 850 FORM COMPLETE) | (1) CERTIFICATION PACKET SUBMISSION TARGET (2) CERTIFICATION PACKET SUBMISSION COMPLETE (3) CERTIFICATION PACKET APPROVAL COMPLETE |  | LICENSURE COMPLETE
LOCATION | CONSUMER NAME | UCI | PLANNED PLACEMENT DATE | DATE OF BIRTH | AGE | CASE WORKER | PROJECTED PROJECT NUMBER | PROPOSED LIVING ARRANGEMENT (Planned Development Type) | PROVIDER | CONSUMER NEEDS DE/SP (YES OR NO) | 290 REGISTRANT (YES OR NO) | EXHIBITS PICA BX's (YES OR NO) | (1) ADMISSION DATE (2) 6500 Commitment Date (if applicable) | LENGTH OF STAY (IN YEARS) | (1) Conserved (Yes or No) (2) Conservator Name | (1) Completed Initial assessment date (2) Last comprehensive assessment date | MEET & GREET | SUCCESSFUL MEET & GREET | TPM (Transition Planning Meeting) | TRM (Transition Review Meeting) | PLACEMENT STATUS (Consumer Movement Status) | PLACEMENT DATE (Consumer Movement Date)
STATE OPERATED FACILITIES
IN ACTIVE TRANSITION
RUNNING PROJECT DEVELOPMENT NOTES
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise::
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise::
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise::
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise::
IN ACTIVE TRANSITION TO A CPP LIVING ARRANGEMENT IN ANOTHER RC'S AREA
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
IN ACTIVE TRANSITION TO A NON-CPP LIVING ARRANGEMENT
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
COMMUNITY ENVIRONMENT NOT YET IDENTIFIED
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
| Proposed living arrangement notes: | [11 empty] | Consumer transition planning updates:
| Barriers identified by the team: | [11 empty] | Planned supports and services-court ordered or otherwise:
PLACED
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
| Proposed living arrangement/Barriers identified by the team notes: | [11 empty] | Consumer transition planning updates/Planned supports and services-court ordered or otherwise:
Formulas:
SPECIALTY AGE GROUP = IF([PROJECT STATUS (ACTIVITY STATUS)]="","", DATEDIF([PROJECT STATUS (ACTIVITY STATUS)],NOW(),"y"))

## OPERATIONS
REGIONAL CENTER OPERATIONS OVERVIEW
# | CPP OPERATION ID | OPERATION TYPE | POSITION STATUS | POSITION CATEGORY | POSITION TITLE | PERSONNEL NAME | DATE OF HIRE | NUMBER OF FTE PROFESSIONAL | NUMBER OF FTE SUPPORT STAFF | NUMBER OF FTE CONSULTANTS | DESCRIPTION